## Product Backlog
Project Name | OpenCart (Front-end)
Client | OpenCart
Created By | Name of the product owner
Creation Date | DD-MM-YYYY
Approval Date | DD-MM-YYYY
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
OpenCart_Epic_001: For a new e-commerce website to launch, the highest business value will be when a new user is able to buy an item from the website | US001 | Registration | As a first time visitor to the e-commerce website, I want to register my account, So that I can login into the application | New | New user should be able to Register account with valid data
| US002 | Login | As a registered user, I want to login into the website, So that I can see my account details | New | System must validate user credentials and allow login if credentials are correct
| US003 | Logout | As a registered user, I want to logout from the website, So that no one else cannot access my account | New | System must logout after login
| US004 | User search products | As a user, I want to be able to search items, So that I can add them into cart and do payment | New | User should able to search products and add them to cart

## Sprint Planning
Project Name | OpenCart (Front-end)
Client | OpenCart
Created By | Name of the product owner
Creation Date | DD-MM-YYYY
Approval Date | DD-MM-YYYY
Epic | User Story ID | Feature/Title | User Story | Story Point | Sprint
OpenCart_Epic_001: For a new e-commerce website to launch, the highest business value will be when a new user is able to buy an item from the website | US001 | Registration | As a first time visitor to the e-commerce website, I want to register my account, So that I can login into the application | 8 | 1
| US002 | Login | As a registered user, I want to login into the website, So that I can see my account details | 5 | 1
| US003 | Logout | As a registered user, I want to logout from the website, So that no one else cannot access my account | 3 | 1
| US004 | User search products | As a user, I want to be able to search items, So that I can add them into cart and do payment | 5 | 1